## Action Tracker
# | Category | Action Item | Owner | Due Date | Status | Notes / Source
1 | Bi-Weekly Sessions | Schedule recurring hands-on session every 2 weeks | Dade |  | Not Started | From 'Making it Real' slide, col 1
2 | Bi-Weekly Sessions | Build and maintain roster of contributors (rotating presenters) | Dade |  | Not Started | From 'Making it Real' slide, col 1
3 | Bi-Weekly Sessions | Contributors lead walkthroughs, hands-on-keyboard format | Rotating contributor |  | Not Started | From 'Making it Real' slide, col 1
4 | Bi-Weekly Sessions | Dry-run each session's content ahead of time to be able to troubleshoot live | Dade |  | Not Started | From 'Making it Real' slide, col 1
5 | Bi-Weekly Sessions | Flag any restrictions / prerequisites (access, licensing, environment) per session | Dade |  | Not Started | From 'Making it Real' slide, col 1
6 | Marketplace Hub | Stand up first-step 'website' marketplace hub for skills and agents (branding TBD) | Dade |  | Not Started | From 'Making it Real' slide, col 2
7 | Marketplace Hub | Wire up backend to GitHub (or other repository) for hub content | Dade |  | Not Started | From 'Making it Real' slide, col 2
8 | Marketplace Hub | Design approval workflow so community can upload contributions subject to review | Dade |  | Not Started | From 'Making it Real' slide, col 2
9 | Marketplace Hub | Set up biweekly update highlighting new/updated/great use cases ('Celebrate great ideas') | Dade |  | Not Started | From 'Making it Real' slide, col 2
10 | AI Hackathon | Craft hackathon scope and send announcement email | Dade & Locky | 2026-08-21 | Not Started | EOD 8/21 per AI Hackathon notes slide
11 | AI Hackathon | Finalize team format: groups of 2-3, no two people from the same immediate team | Locky |  | Not Started | Locky's proposal, per notes slide
12 | AI Hackathon | Define project judging criteria: AI sophistication, vision for scale, hypothesis on company impact (cost/time/effort savings or quality gain) | Dade & Locky |  | Not Started | Per notes slide
13 | AI Hackathon | Plan presentation timing at team week (e.g., ~10 min per team across ~8 teams) | Dade & Locky |  | Not Started | Per notes slide
14 | AI Hackathon | Decide scoring approach and confirm judges (Mike? Jessica? Takeshi?) | Dade & Locky |  | Not Started | Per notes slide
15 | AI Hackathon | Confirm prize budget/details with Maria | Dade |  | Not Started | 'Huge prizes from Maria' on Making it Real slide
16 | AI Hackathon | Confirm dinner prize with Jessica (she doesn't know yet) | Dade |  | Not Started | Flagged on Making it Real slide
17 | AI Hackathon | Leave winner/prize structure open for Locky to finalize | Locky |  | Not Started | Per notes slide